## PDA
Branch | Program | Comp etitive | Acq Strategy | POP | Planned RFP | Actual RFP | Planned Award | Actual Award | $ | Current Contractor or OEM | PALT Updates | Change
GT | Tower Simulation Systems (TSS) Block Upgrade | No | Sole Source | 2 Yrs | JAN 2027 Q1FY27 |  | JUL 2027 Q3FY27 |  | $7M | UFA, Inc
GT | NITE Lab Night Scene Simulator (NSS) Upgrade | No | Sole Source | 2 Yrs | Q1FY28 |  | Q3FY28 |  | $2M | Aechelon
GT | Modular Egress Training System (METS) Modernization | No | Sole Source | 1 Yr | Q1FY29 |  | Q3FY29 |  | $1.5M | Survival Systems USA
GT | Shore Based Air Traffic System (SATS) Upgrade | No | Sole Source | 3 Yrs | Q2FY29 |  | Q3FY29 |  | $6.5M | Symvionics Inc
NT | P-8 OFT Projector Tech Refresh (FY26) | Yes | Competitive | 2 Yrs | MAY 2026 | MAY 2026 | SEP 2026 |  | $10M | Boeing
NT | F/A-18 TOFT SCS/OFP Concurrency (FY26) | No | Sole Source | 2 Yrs | NOV 2025 | NOV 2025 | SEP 2026 |  | $19.7M | Boeing
NT | MH-60 Tech Refresh - Cyber & CM | No | Sole Source | 20 Mo | Option Exercise | N/A | NOV 2026 |  | $1.5M | JFTI
NT | MH-60R/S Tech Refresh (Visual Systems) | No | Sole Source | 2 Yrs | SEP 2026 |  | MAR 2027 Q3FY27 |  | $10M | JFTI
NT | MH-60R/S MX Tech Refresh (CMT/AFCS/WLT) | No | Sole Source | 2 Yrs | SEP 2026 |  | MAR 2027 |  | $8M | JFTI
NT | MH-60R/S MX Tech Refresh (AMT) | No | Sole Source | 2 Yrs | MAY 2027 |  | SEP 2027 Q4FY27 |  | $20M | JFTI
NT | E-6B Tech Refresh | No | Sole Source | 16 Mo | JAN 2027 |  | JUN 2027 |  | $2M | Fidelity Tech
NT | TH-73 Mixed Reality Upgrade | No | Sole Source | 2 Yrs | JUN 2026 |  | SEP 2026 AUG 2026 |  | $8M | Katmai | Sole source via Army Contracting Command to SAIC (Hardware in the Loop). | x
NT | T-45 Strike Refresh - UPS | No | Sole Source | 1 Yr | JUL 2026 |  | SEP 2026 AUG 2026 |  | $2M | Katmai | Sole source via Army Contracting Command to SAIC (Hardware in the Loop). | x
NT | E-2D Tech Refresh (Operating Systems) | No | Sole Source | 2 Yrs | JUN 2027 |  | Q3FY28 |  | $2.5M | Collins
NT | P-8 Tech Refresh (Single Board Computer) | No | Sole Source | 2 Yrs | JAN 2027 SEP 2026 |  | SEP 2027 Q4FY27 |  | $5M | Boeing |  | x
NT | P-8 Tech Refresh (IG & Network Switches) | No | Sole Source | 1 Yr | MAR 2027 |  | JUN 2027 |  | $5M | Boeing
NT | F/A-18 TOFT SCS/OFP Concurrency (FY27) | No | Sole Source | 1 Yr | MAR 2027 |  | SEP 2027 Q4FY27 |  | $15M | Boeing
NT | F/A-18 Cyber & CM | No | Sole Source | 1 Yr | OCT 2026 |  | MAR 2027 |  | $2M | Boeing
NT | F/A-18 TOFT Win 11 Updates (HW) | No | Sole Source | 2 Yrs | NOV 2025 | NOV 2025 | SEP 2026 |  | $40M | Boeing
USMC | CH-53K Tech Refresh | Yes | Full and Open | 5 Yrs | JAN 2027 NOV 2026 |  | Q4FY27 |  | $205M | ByLIght / Veraxx | Aligning RFP Release with FY27 staffing plan | x
USMC | Aviation Distribution Virtual Training Environment (ADVTE) II | Yes | Full and Open | 5 Yrs | JUN 2027 Q3FY27 |  | Q2FY28 |  | $45M | ByLIght / Veraxx
USMC | Marine Common Aircrew Trainer (MCAT) Mixed Reality Trainer (MRT) Program | Yes | OTA | TBD | MAR 2026 | MAR 2026 | DEC 2026 |  | $7M | Kratos / Cymstar | Award Dec 26 via Naval Aviation Systems Consortium (NASC)
USMC | H-1 Training Device Modernization Program II (Lot 9/10) | Yes | Full and Open | TBD | TBD Q2FY27 |  | TBD Q1FY28 |  | $75M | Bell Textron/FSI | Lack of funding in FY28, Procurement awaiting POM Issue Sheet Approval | x
USMC | V-22 Training Device Moderization Program (TDMP) | Yes | TBD | TBD | Q1FY28 |  | Q3FY28 |  | $70M | ByLIght / Veraxx | Acquisition Strategy under development
USMC | ADVTE DO 5 | No | Sole Source | 1.5 Yr | JAN 2026 | FEB 2026 | JUL 2026 | AUG 2026 | $4M | ByLIght / Veraxx | Awarded | x
USMC | TEn TUC DO 4 | No | Sole Source | 1.5 Yr | MAY 2026 | MAY 2026 | SEP 2026 JUL 2026 |  | $2M | ByLIght / Veraxx |  | x
USMC | USMC H-1 Cockpit Procedures Trainer (CPT) Modernization | Yes | TBD | 2 Yrs | TBD |  | TBD |  | $1M | N/A | Delayed due to funding
VIT | CASE Fidelity Enhancements | No | SBIR | 5 yr | OCT 2026 |  | JAN 2027 |  | $1M | AAC

## PDS&U
Branch | Program | Comp etitive | Acq Strategy | POP | Planned RFP | Actual RFP | Planned Award | Actual Award | $ | Current Contractor | PALT Updates | Column1
PDS | Surface Firefighting and Damage Control Trainer Modernization (Mayport) Phase 3 | TBD No | TBD | TBD | Q1FY27 MAY 2026 |  | Q2FY27 Q3FY26 |  | TBD | N/A | Current strategy is for PMS339 to use an existing NAVSEA contract vehicle.
PDS | PC-Based Open-Architecture for Reconfigurable Training Systems (PORTS) | No | TBD | 5 Yrs | Q1FY27 Q3FY26 |  | Q2FY27 Q4FY26 |  | TBD | Northrop Grumman / Serco
PDS | Engineering Contractor Instructor Services (ECIS) | Yes | FTSS V, Lot II Restricted | 64 Mo | JUL 2026 | JUL 2026 | Q1FY27 |  | TBD | Prevailance
PDS | Pacific NorthWest (PACNORWEST) FireFighting and Damage Control Instructor Services | Yes | TBD | 6 Yrs | NOV 2026 OCT 2026 |  | APR 2027 FEB 2027 |  | TBD | WRG | Routing request for approval to make this a 6 Yr contract.
PDS | Aegis Ashore Team Trainer (AATT) | No | SBIR | 5 Yrs | MAY 2026 |  | SEP 2026 Q4FY26 |  | TBD | GO Precise | A3C4I upgrades to match AATT to Host Nations.
PDS | Site Activation | No | 8(a) Alaskan Native / Indian Tribe Anticipated | 5 Yrs | SEP 2026 |  | FEB 2027 |  | $99M | N/A
PDS | Surface Firefighting and Damage Control Trainer Modernization | TBD | TBD | TBD | Q4FY28 |  | Q2FY29 |  | TBD | N/A | (Sites to be included are TBD)
PDS | Next Generation Surface Search Radar (NGSSR) Maintenance Course Development | No | STTR | 1 Yr |  | JUN 2026 | AUG 2026 | AUG 2026 | $600K | Soar Tech | Awarded to Soar Tech
PDS | Aegis Training Support Services (Follow-on) | No | Sole Source | 5 Yrs | Q4FY27 |  | Q2FY28 |  | TBD | Lockheed Martin
PDS | Surface Training Readiness Management Software (STRMS) (Follow-on) | No | SBIR | 5 Yrs | Q3FY27 |  | Q1FY28 |  | TBD | General Dynamics
PDS | Next-Generation Mission Readiness AI-Powered Transformation Tool | No | OTA | TBD | Q1FY27 |  | Q2FY27 |  | TBD | Ethos Technologies | Production follow-on to initial OTA for N96.

## PDX
Branch | Program | Comp etitive | Acq Strategy | POP | Planned RFP | Actual RFP | Planned Award | Actual Award | $ | Current Contractor | PALT Updates | Change
CTC | Career Training Continuum - Performance Support Career Long Learning Continuum (CLLC) 1st Increment Prize Challenge | Yes | Prize Challenge | 5 Yrs | AUG 2026 | AUG 2026 | NOV 2026 OCT 2026 |  | Prize Challenge: $55K, $30K, $20K Contract Award Estimate: $20M | N/A | Prize Challenge released with Phase 1 deadline of 25 SEP. Phase 2 and 3 downselects will take place in OCT and NOV with final Phase 3 selection of winners on 05 NOV. Subsequent contract award following prize challenge will be dependent on vendor selected with plan to award NLT FEB 2027. | x
CTC | Career Training Continuum - Requirements Development (RD) Contract NAVIFOR Career Long Learning Continuum (CLLC) TS SCI | No | 8(a) Anticipated | 3 Yrs | OCT 2026 SEP 2026 |  | DEC 2026 |  | $5M | N/A | Planned RFP shifted one month to OCT. | x
CTC | Career Training Continuum - Content Conversion (IT) | No | 8(a) Sole Source | 2 Yrs 3 Yrs | OCT 2026 |  | NOV 2026 |  | $6.5M $9.5M | N/A | Modified POP to expected delivery timeline and refined funding estimate planned for this effort. | x
TS | Chief of Naval Air Training (CNATRA) Contractor Operation and Maintenance Services (COMS)​ | Yes | FTSS V Lot 1 | 5Yrs | FEB 2026 | JAN 2026 | AUG 2026 | AUG 2026 | $45M | Fidelity Technologies Services | Awarded to Fidelity Technologies Services | x
TS | Maritime Contractor Operations and Maintenance Services (COMS) | Yes | FTSS V Lot 1 | 5Yrs | SEP 2026 AUG 2026 |  | MAR 2027 |  | $90M | Valiant Global Defense | Shifted RFP release to SEP. | x
TS | Naval Aviation Technical Training Center (NATTC) Contractor Operations and Maintenance Services (COMS) and Contractor Instructional Services (CIS) | Yes | FTSS V Lot 2 | 5 Yrs | MAR 2027 Q3FY28 |  | Q1FY28 Q4FY28 |  | $41M | ESP, Inc | Accelerated acquisition strategy and modified current contract PoP to enable execution under FTSS V. | x
TS | Command Aircraft Crew Training C-40A Pilot | Yes | SBSA Full & Open | 5 Yrs | OCT 2026 |  | Q2FY27 |  | $9M | BMA | Contract determined to be SBSA. | x
TSC | Pilot and Aircrew Revision and Maintenance (R&M) Multiple Award Contract II (PACRM II) | Yes | SDVOSB | 11 Yrs | FEB 2026 | JUL 2026 | MAY 2027 NOV 2026 |  | $322M | MilTrain, BGI, AHA, and Carley | Due to ceiling increase in PACRM I and strategy change for USMC R&M, award date has been adjusted to MAY 2027. | x
TSC | Pilot and Aircrew Courseware R&M - USMC​ | Yes | PACRM I | 5 Yrs | SEP 2026 AUG 2026 |  | MAR 2027 |  | $36M | MilTrain | Shifted RFP release to SEP due to discussions with sponsor to lock in the requirements. | x
TSC | Pilot and Aircrew Courseware Revision and Maintenance (R&M) - E-2/LSO | Yes | PACRM I | 5 Yrs | JUN 2026 | JUN 2026 | SEP 2026 AUG 2026 |  | $2M | A. Harold and Associates | Award planned for late SEP. | x
TSC | USMC Ground Training Systems Support (GTSS)-OCONUS | Yes No | 8(a) Competitive 8(a) Sole Source | 5 Yrs | Q3FY28 |  | Q2FY29 Q1FY29 |  | $35M | Katmai Inc. | Updated acquisition strategy to competive remaining within the 8(a) program while aligning award date to deconflict multiple priorities at that time. | x
CTC | Career Training Continuum - Requirements Development (RD) Career Long Learning Continuum (CLLC) Contract | No | 8(a) Sole Source | 5 Yrs | OCT 2026 |  | DEC 2026 |  | $40M | Yulista
TS | Fielded Training Systems Support FTSS VI | Yes | TBD | 5 Yrs | Q1FY27 |  | Q1FY28 |  | $2.8B | Multiple: 7 Lot 1 Contractors; 2 Lot 2 Contractors
TS | Command Aircraft Crew Training UC-35 | No | Sole Source anticipated | 5 Yrs | JUN 2026 | JUN 2026 | NOV 2026 |  | $9M | FSI
TS | Western Pacific (WESTPAC) Contractor Operation & Maintenance Services (COMS) | Yes | FTSS V Lot 1 | 5 Yrs | Q3FY27 |  | Q2FY28 |  | $19M | Fidelity Technologies Services
TS | Chief of Naval Air Training (CNATRA) Contractor Instructor Services (CIS)​ | Yes | FTSS V Lot 1 | 5 Yrs | Q3FY27 |  | Q3FY28 |  | $365M | Fidelity Technologies Services
TS | Navy Helicopter COMS / CIS | Yes | FTSS VI Lot 1 | 5 Yrs | Q2FY28 |  | Q1FY29 |  | $130M | Fidelity Technologies Services
TS | TH-73 Aviation Training Systems (ATS) | TBD | TBD | 6 Yrs | Q2FY28 |  | Q4FY28 |  | $75M | Flight Safety International
TSC | Pilot and Aircrew Courseware R&M - Strike Fighter/Electronic Warfare | Yes | PACRM II | 5 Yrs | Q3FY27 |  | Q1FY28 |  | $23M | MilTrain
TSC | Pilot and Aircrew Courseware R&M - Maritime | Yes | PACRM II | 5 Yrs | Q2FY27 |  | Q4FY27 |  | $9M | MilTrain
TSC | Pilot and Aircrew Courseware R&M - Navy Helo | Yes | PACRM II | 5 Yrs | Q2FY29 |  | Q4FY29 |  | $28M | MilTrain
TSC | Merge, Manage & Modernize E-Learning Development (MELD) Software Suite Support | Yes | TBD | 5 Yrs | Q1FY29 |  | Q4FY29 |  | $4.5M | CT3I, JV
TSC | Small Arms Marksmanship Trainer (SAM-T) | TBD | TBD | 10 Months | MAR 2027 |  | JUL 2027 |  | $2.5M | N/A
TSC | USMC Ground Training Systems Support (GTSS)-West | Yes | 8(a) Competitive | 5 Yrs | Q1FY28 |  | Q1FY29 |  | $75M | Katmai Inc.

## PDI
Branch | Program | Comp etitive | Acq Strategy | POP | Planned RFP | Actual RFP | Planned Award | Actual Award | $ | Current Contractor | PALT Updates | Change | Column2
PDI | Nigeria Air Force (NAF) AH-1Z Flight Training Device (FTD) | No | Sole Source | 2 Yrs | JUL 2024 | JUL 2024 | AUG 2026 | 26 AUG 2026 | $21M | Bell Textron | Awarded to Bell Textron |  | x
PDI | Czech Republic UH-1Y Flight Training Device (FTD) | No | Sole Source | 2 Yrs | JUL 2025 | 1 JUL 2025 | DEC 2026 OCT 2026 |  | $20M | Bell Textron |  |  | x
PDI | Canada P-8A Aircrew and Maintenance Training Systems | No | Sole Source | 6 Yrs | SEP 2024 | AUG 2024 | Q3FY27 |  | $600M | Boeing |  | X
PDI | Denmark (DALO) MH-60R MOFT Follow-on contractor operator maintenance support | No | Sole Source | 5 Yrs | JAN 2026 | JAN 2026 | OCT 2026 |  | $8M | CAE
PDI | Taiwan P-3C Weapons System Trainer (WST) Tech Refresh | No | Sole Source | 3 Yrs | AUG 2026 | 18 AUG 2026 | APR 2027 Q2FY27 |  | $20M | CAE |  | X
PDI | ROKN P-8A Contractor Logistics Support (CLS) | No | Sole Source | 2 Yrs | APR 2026 | MAR 2026 | Q3FY27 |  | $18M | Boeing
PDI | Kuwait KC-130J Pilot, Aircrew and Maintainer Instructional Services Follow On IDIQ | No | Sole Source | 5 Yrs | MAY 2026 | MAY 2026 | MAR 2027 |  | $61M | Aviation Training Consulting
PDI | Republic Of Korea Navy (ROKN) MH-60R TOFT CLS | No | Sole Source | 4 Yrs | JUL 2026 | 25 JUN 2026 | MAY 2027 FEB 2027 |  | $8M | CAE
PDI | Canada P-8A Aircrew Training Systems Common Acoustic Simulation Environment Fidelity Implementation (CASEFI) CASE 2D Propogation Optimization (C2PO) software and hardware | No | Sole Source | 4.5 Yrs | JUL 2026 | 13 JUL 2026 | MAR 2027 Q2FY27 |  | $25M | Advanced Acoustics Concepts, LLC
PDI | Kuwait F/A-18 Contractor Instructional Services (CIS) follow on | No | Sole Source | 5 Yrs | AUG 2026 | 7 AUG 2026 | Q4FY27 Q2FY27 |  | $58M | Boeing
PDI | Singapore P-8A Aircrew and Maintenance Training Systems | No | Sole Source | 5 Yrs | 30 SEP 2026 AUG 2026 |  | DEC 2028 |  | $234M | Boeing
PDI | Royal Australian Navy MH-60R Maintenance Trainers Upgrade - AMWLT, AFCST & CMT SC26/SC28 upgrade, TECRs | No | Sole Source | 5 Yrs | Q4FY28 |  | Q2FY29 |  | $10M | CAE
PDI | Indian Navy MH-60R Tactical Operational Flight Trainer (TOFT) & Avionics Maintenance Weapons Load trainer (AMWLT) Trainer Contractor Logistics Support (CLS) | No | Sole Source | 5 Yrs | TBD |  | Q4FY27 |  | $8M | CAE
PDI | Royal Saudi Naval Forces (RSNF) MH-60R Contractor Operation and Maintenance Services (COMS) and Contractor Instructor Services (CIS) | TBD | TBD | 5 Yrs | Q4FY28 |  | Q2FY29 |  | TBD | Valiant Global Defense | Directed sole-source or FTSS VI

## PD Legend
PD | Branch | Description
PDA
| NT | Navy Training
| USMC | Marine Corps
| GT | General Training
PDSU
| PDS | Surface
| PDU | Undersea
PDX
| TS | Training Services
| TSC | Training Systems and Content
| CTC | Career Training Continuum
PDI
| PDI | International
PDRT |  | Research & Technology